## Sheet1
Tasks waiting to be completed: | Worked by: | Date and hour started | Minutes worked |  | Not started | Member | Minutes | Hours
Project plan v1 | Georgi and Ilia | 19.02. ¦¦ 14:20 | 100 | Week 2 | Being worked on | Angel | 1420 | 23:40 | 17% |  | Angel | Georgi | Ilia | Mikaeil
Group logo | Mikaeil | 21.02. ¦¦ 19:10 | 120 |  | Completed | Georgi | 2001 | 33:21 | 24% | Angel | 1420 | 120 | 0 | 0
Base documents (agenda, notes and meeting) | Georgi | 23.02. ¦¦ 15:30 | 60 |  |  | Ilia | 2656 | 44:16 | 32% | Georgi |  | 2001 | 601 | 200
DOT research Framework | Group | 25.02. ¦¦ 15:00 | 60 |  |  | Mikaeil | 2310 | 38:30 | 28% | Ilia |  |  | 2656 | 380
SVN:Google code | Ilia | 26.02. ¦¦ 15:50 | 5 |  |  | as a Group | 475 | 7:55 | 6% | Mikaeil |  |  |  | 2310
Phidgit Authenticator testing | Ilia | 02.03. ¦¦ 16:45 | 65 |  |  | Total | 8387 | 139:47
Base documents (agenda, notes and meeting) | Georgi | 05.03. ¦¦ 17:20 | 50 | Week 3
Process report | Georgi | 05.03. ¦¦ 18:10 | 90
Project plan v2 | Georgi and Ilia and Mikaeil | 06.03. ¦¦ 15:00 | 120
Website design/code | Angel | 07.03. ¦¦ 14:20 | 60
Event ERD | Mikaeil and Ilia | 9.03. ¦¦ 10:40 | 40 | Week 4
Project plan v2 | Ilia | 10.03. ¦¦ 20:00 | 180
Initial application setup | Ilia | 10.03. ¦¦ 19:00 | 60
Paypal converter for C# | Ilia | 10.03. ¦¦ 23:20 | 10
Project plan v2 | Ilia | 11.03. ¦¦ 18:48 | 120
Research on future tech | Ilia | 11.03. ¦¦ 22:00 | 60
Base documents (agenda, notes and meeting) | Georgi | 12.03. ¦¦ 16:10 | 60
Database design and implementation | Mikaeil | 12.03. ¦¦19:00 | 60
Graphical design | Mikaeil | 12.03. ¦¦ 20:00 | 30
User interface | Mikaeil | 12.03. ¦¦ 20:30 | 40
Tasks file interface improvement | Ilia and Georgi | 13.03. ¦¦ 16:40 | 61
Transfer to GITHub | Ilia | 14.03. ¦¦ 02:10 | 5
Process report | Georgi | 14.03. ¦¦ 02:40 | 60
Group meeting | Georgi, Mikaeil and Ilia | 16.03. ¦¦ 11:00 | 40 | Week 5
Base documents (agenda, notes and meeting) | Georgi | 17.03. ¦¦ 16:00 | 40
Group meeting | Georgi, Mikaeil and Ilia | 18.03. ¦¦ 12:20 | 40
Wireframe | Angel | 21.03. ¦¦ 15:30 | 60
Database design and implementation | Mikaeil | 21.03. ¦¦ 15:30 | 120
Website design | Angel | 21.03. ¦¦ 16:30 | 60
Setup document v1 | Georgi and Ilia | 21.03. ¦¦ 17:00 | 120
Group meeting | Group | 23.03. ¦¦ 11:00 | 40 | Week 6
Database design and implementation | Mikaeil | 23.03. ¦¦ 11:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 23.03. ¦¦ 10:30 | 120
Application GUI | Mikaeil and Ilia | 23.03. ¦¦ 11:00 | 140
Setup document v2 | Georgi | 23.03. ¦¦ 11:10 | 100
GUI design | Ilia | 23.03. ¦¦ 09:00 | 120
Website wireframe | Angel | 23.03. ¦¦ 13:20 | 60
Database design and implementation | Mikaeil | 24.03. ¦¦ 13:00 | 120
GUI design | Ilia | 25.03. ¦¦ 20:00 | 120
Database review | Ilia | 25.03. ¦¦ 22:00 | 30
Website frontpage | Angel | 25.03. ¦¦ 16:00 | 180
Website review | Angel and Georgi | 26.03. ¦¦ 12:00 | 40
Database utilities | Ilia | 27.03. ¦¦ 10:00 | 140
Website | Angel | 28.03. ¦¦ 07:30 | 210
Database helper | Ilia | 28.03. ¦¦ 12:30 | 180
Database helper | Ilia | 29.03. ¦¦ 11:20 | 60 | Week 7
Setup document | Ilia and Georgi | 30.03. ¦¦ 08:10 | 120
Setup document | Ilia | 30.03. ¦¦ 10:30 | 60
Base documents (agenda, notes and meeting) | Georgi | 31.03. ¦¦ 10:30 | 10
Website implementation | Angel | 01.04. ¦¦ 15:30 | 60
Setup document | Georgi | 12.04. ¦¦ 05:40 | 60 | Week 9
Base documents (agenda, notes and meeting) | Georgi | 12.04. ¦¦ 08:30 | 60
GUI design | Mikaeil | 13.04. ¦¦ 16:30 | 180
Website implementation | Angel | 15.04. ¦¦ 12:00 | 120
Map feature | Ilia | 16.04. ¦¦ 8:30 | 60
Map zoom | Ilia | 16.04. ¦¦ 11:30 | 30
Programming | Mikaeil | 16.04. ¦¦ 11:00 | 180
Website implementation | Angel | 17.04. ¦¦ 12:00 | 120
Map translation | Ilia | 17.04. ¦¦ 01:30 | 60
Process report | Georgi | 17.04. ¦¦ 12:00 | 180
Setup document | Georgi | 18.04. ¦¦ 13:00 | 60
GUI design | Mikaeil | 18.04. ¦¦ 13:00 | 180
Map search function | Ilia | 18.04. ¦¦ 04:30 | 120
Menu Inheritance | Ilia | 19.04. ¦¦ 10:30 | 150
GUI design | Mikaeil | 19.04. ¦¦ 16:30 | 180
Website implementation | Angel | 19.04. ¦¦ 12:00 | 120
Group meeting | Group | 20.04. ¦¦ 10:30 | 165 | Week 10
GUI design | Mikaeil | 20.04. ¦¦ 13:00 | 180
Website design | Angel | 21.04. ¦¦ 12:00 | 120
Group meeting | Group | 22.04. ¦¦ 13:30 | 120
Setup document | Angel | 23.04. ¦¦ 19:00 | 30
Website | Angel | 23.04. ¦¦ 19:30 | 100
Setup document review | Georgi | 23.04. ¦¦ 21:00 | 60
Database SQL | Ilia | 23.04. ¦¦ 20:00 | 120
GUI design | Mikaeil | 23.04. ¦¦ 13:00 | 180
Classes | Ilia | 23.04. ¦¦ 22:00 | 120
Schedule and website review | Georgi and Angel | 24.04. ¦¦ 11:30 | 80
Setup document | Georgi | 24.04. ¦¦ 12:40 | 30
Group meeting: Schedule, Setup document, Website, GitHub | Group | 24.04. ¦¦ 16:30 | 90
Database | Mikaeil | 24.04. ¦¦ 17:00 | 60
Database research | Georgi | 25.04. ¦¦ 12:00 | 180
Programming | Mikaeil | 26.04. ¦¦ 12:00 | 180
Base documents (agenda, notes and meeting) | Georgi | 28.04. ¦¦ 18:30 | 60 | Week 11