## Sheet1
Tasks waiting to be completed: | Worked by: | Date and hour started | Minutes worked |  | Not started | Member | Minutes | Hours
Project plan v1 | Georgi and Ilia | 19.02. ¦¦ 14:20 | 100 | Week 2 | Being worked on | Angel | 60 | 1 | 3% |  | Angel | Georgi | Ilia | Mikaeil
Group logo | Mikaeil | 21.02. ¦¦ 19:10 | 120 |  | Completed | Georgi | 541 | 9.02 | 29% | Angel | 60 | 0 | 0 | 0
Base documents (agenda, notes and meeting) | Georgi | 23.02. ¦¦ 15:30 | 60 |  |  | Ilia | 826 | 13.77 | 45% | Georgi |  | 541 | 281 | 120
DOT research Framework | Group | 25.02. ¦¦ 15:00 | 60 |  |  | Mikaeil | 410 | 6.83 | 22% | Ilia |  |  | 826 | 160
SVN:Google code | Ilia | 26.02. ¦¦ 15:50 | 5 |  |  | as a Group | 60 | 1 | 3% | Mikaeil |  |  |  | 410
Phidgit Authenticator testing | Ilia | 02.03. ¦¦ 16:45 | 65 |  |  | Total | 1837 | 30.62
Base documents (agenda, notes and meeting) | Georgi | 05.03. ¦¦ 17:20 | 50 | Week 3
Process report | Georgi | 05.03. ¦¦ 18:10 | 90
Project plan v2 | Georgi and Ilia and Mikaeil | 06.03. ¦¦ 15:00 | 120
Website design/code | Angel | 07.03. ¦¦ 14:20 | 60
Event ERD | Mikaeil and Ilia | 9.03. ¦¦ 10:40 | 40 | Week 4
Project plan v2 | Ilia | 10.03. ¦¦ 20:00 | 180
Initial application setup | Ilia | 10.03. ¦¦ 19:00 | 60
Paypal converter for C# | Ilia | 10.03. ¦¦ 23:20 | 10
Project plan v2 | Ilia | 11.03. ¦¦ 18:48 | 120
Research on future tech | Ilia | 11.03. ¦¦ 22:00 | 60
Base documents (agenda, notes and meeting) | Georgi | 12.03. ¦¦ 16:10 | 60
Database design and implementation | Mikaeil | 12.03. ¦¦19:00 | 60
Graphical design | Mikaeil | 12.03. ¦¦ 20:00 | 30
User interface | Mikaeil | 12.03. ¦¦ 20:30 | 40
Tasks file interface improvement | Ilia and Georgi | 13.03. ¦¦ 16:40 | 61
Transfer to GITHub | Ilia | 14.03. ¦¦ 02:10 | 5
Process report | Georgi | 14.03. ¦¦ 02:40