## Sheet1
Tasks waiting to be completed: | Worked by: | Date started and finished | Minutes worked | Not started
Group logo | Mikaeil | 21.02. - | 120 | Being worked on
Project plan v1 | Group | 21.02-02.03 | 100 | Completed
Project plan v2 | Group | 04.03.- | 480
Google code | Ilia | 26.02-26.02 | 5
Framework | Group | 25.02.-25.02. | 60
Base documents (agenda, notes and meeting) | Georgi | 23.02.- | 110
Authenticator testing | Ilia | 03.03. | 40
Website design/code | Angel | 07.03- | 60
Event ERD | Mikaeil and Ilia | 9.03 | 40
Process report | Georgi | 05.03. | 90
Initial application setup | Ilia | 10.03. | 60
Paypal converter for C# | Ilia | 10.03. | 10
Research on future tech | Ilia | 10.03. | 60