## Sheet1
Tasks waiting to be completed: | Worked by: | Date and hour started | Minutes worked | Not started | Member | Minutes | Hours
Group logo | Mikaeil | 21.02. ¦¦ ? | 120 | Being worked on | Angel | 60 | 1
Project plan v1 | Ilia | 21.02-02.03 ¦¦ ? | 100 | Completed | Georgi | 420 | 7
Project plan v1 | Georgi | 21.02-02.03 ¦¦ ? | 100 |  | Ilia | 735 | 12.25
Project plan v2 | Georgi | 06.03. ¦¦ 15:00 | 120 |  | Mikaeil | 160 | 2.67
Project plan v2 | Ilia | 06.03. ¦¦ 15:00 | 120 |  | Total | 1375 | 22.92
Project plan v2 | Ilia | 10.03. ¦¦ 20:00 | 180 |  | as a Group | 60 | 1
Project plan v2 | Ilia | 11.03. ¦¦ 18:48 | 120
Project plan v2 | Mikaeil | 06.03. ¦¦ 15:00 | 0
Google code | Ilia | 26.02. ¦¦ ? | 5
Framework | Group | 25.02. ¦¦ ? | 60
Base documents (agenda, notes and meeting) | Georgi | 23.02. ¦¦ ? | 110
Authenticator testing | Ilia | 03.03. ¦¦ ? | 40
Website design/code | Angel | 07.03. ¦¦ ? | 60
Event ERD | Mikaeil and Ilia | 9.03. ¦¦ ? | 40
Process report | Georgi | 05.03. ¦¦ ? | 90
Initial application setup | Ilia | 10.03. ¦¦ ? | 60
Paypal converter for C# | Ilia | 10.03. ¦¦ ? | 10
Research on future tech | Ilia | 10.03. ¦¦ ? | 60