## Sheet1
Tasks waiting to be completed: | Worked by: | Date and hour started | Minutes worked |  | Not started | Member | Minutes | Hours
Project plan v1 | Georgi and Ilia | 19.02. ¦¦ 14:20 | 100 | Week 2 | Being worked on | Angel | 3460 | 57:40 | 24% |  | Angel | Georgi | Ilia | Mikaeil
Group logo | Mikaeil | 21.02. ¦¦ 19:10 | 120 |  | Completed | Georgi | 3591 | 59:51 | 25% | Angel | 3460 | 300 | 360 | 60
Base documents (agenda, notes and meeting) | Georgi | 23.02. ¦¦ 15:30 | 60 |  |  | Ilia | 4496 | 74:56 | 31% | Georgi |  | 3591 | 901 | 200
DOT research Framework | Group | 25.02. ¦¦ 15:00 | 60 |  |  | Mikaeil | 3010 | 50:10 | 21% | Ilia |  |  | 4496 | 440
SVN:Google code | Ilia | 26.02. ¦¦ 15:50 | 5 |  |  | as a Group | 955 | 15:55 | 7% | Mikaeil |  |  |  | 3010
Phidgit Authenticator testing | Ilia | 02.03. ¦¦ 16:45 | 65 |  |  | Total | 14557 | 242:37
Base documents (agenda, notes and meeting) | Georgi | 05.03. ¦¦ 17:20 | 50 | Week 3
Process report | Georgi | 05.03. ¦¦ 18:10 | 90
Project plan v2 | Georgi and Ilia and Mikaeil | 06.03. ¦¦ 15:00 | 120
Website design/code | Angel | 07.03. ¦¦ 14:20 | 60
Event ERD | Mikaeil and Ilia | 9.03. ¦¦ 10:40 | 40 | Week 4
Project plan v2 | Ilia | 10.03. ¦¦ 20:00 | 180
Initial application setup | Ilia | 10.03. ¦¦ 19:00 | 60
Paypal converter for C# | Ilia | 10.03. ¦¦ 23:20 | 10
Project plan v2 | Ilia | 11.03. ¦¦ 18:48 | 120
Research on future tech | Ilia | 11.03. ¦¦ 22:00 | 60
Base documents (agenda, notes and meeting) | Georgi | 12.03. ¦¦ 16:10 | 60
Database design and implementation | Mikaeil | 12.03. ¦¦19:00 | 60
Graphical design | Mikaeil | 12.03. ¦¦ 20:00 | 30
User interface | Mikaeil | 12.03. ¦¦ 20:30 | 40
Tasks file interface improvement | Ilia and Georgi | 13.03. ¦¦ 16:40 | 61
Transfer to GITHub | Ilia | 14.03. ¦¦ 02:10 | 5
Process report | Georgi | 14.03. ¦¦ 02:40 | 60
Group meeting | Georgi, Mikaeil and Ilia | 16.03. ¦¦ 11:00 | 40 | Week 5
Base documents (agenda, notes and meeting) | Georgi | 17.03. ¦¦ 16:00 | 40
Group meeting | Georgi, Mikaeil and Ilia | 18.03. ¦¦ 12:20 | 40
Wireframe | Angel | 21.03. ¦¦ 15:30 | 60
Database design and implementation | Mikaeil | 21.03. ¦¦ 15:30 | 120
Website design | Angel | 21.03. ¦¦ 16:30 | 60
Setup document v1 | Georgi and Ilia | 21.03. ¦¦ 17:00 | 120
Group meeting | Group | 23.03. ¦¦ 11:00 | 40 | Week 6
Database design and implementation | Mikaeil | 23.03. ¦¦ 11:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 23.03. ¦¦ 10:30 | 120
Application GUI | Mikaeil and Ilia | 23.03. ¦¦ 11:00 | 140
Setup document v2 | Georgi | 23.03. ¦¦ 11:10 | 100
GUI design | Ilia | 23.03. ¦¦ 09:00 | 120
Website wireframe | Angel | 23.03. ¦¦ 13:20 | 60
Database design and implementation | Mikaeil | 24.03. ¦¦ 13:00 | 120
GUI design | Ilia | 25.03. ¦¦ 20:00 | 120
Database review | Ilia | 25.03. ¦¦ 22:00 | 30
Website frontpage | Angel | 25.03. ¦¦ 16:00 | 180
Website review | Angel and Georgi | 26.03. ¦¦ 12:00 | 40
Database utilities | Ilia | 27.03. ¦¦ 10:00 | 140
Website | Angel | 28.03. ¦¦ 07:30 | 210
Database helper | Ilia | 28.03. ¦¦ 12:30 | 180
Database helper | Ilia | 29.03. ¦¦ 11:20 | 60 | Week 7
Setup document | Ilia and Georgi | 30.03. ¦¦ 08:10 | 120
Setup document | Ilia | 30.03. ¦¦ 10:30 | 60
Base documents (agenda, notes and meeting) | Georgi | 31.03. ¦¦ 10:30 | 10
Website implementation | Angel | 01.04. ¦¦ 15:30 | 60
Setup document | Georgi | 12.04. ¦¦ 05:40 | 60 | Week 9
Base documents (agenda, notes and meeting) | Georgi | 12.04. ¦¦ 08:30 | 60
GUI design | Mikaeil | 13.04. ¦¦ 16:30 | 180
Website implementation | Angel | 15.04. ¦¦ 12:00 | 120
Map feature | Ilia | 16.04. ¦¦ 8:30 | 60
Map zoom | Ilia | 16.04. ¦¦ 11:30 | 30
Website implementation | Angel | 17.04. ¦¦ 12:00 | 120
Map translation | Ilia | 17.04. ¦¦ 01:30 | 60
Process report | Georgi | 17.04. ¦¦ 12:00 | 180
Setup document | Georgi | 18.04. ¦¦ 13:00 | 60
GUI design | Mikaeil | 18.04. ¦¦ 13:00 | 180
Map search function | Ilia | 18.04. ¦¦ 04:30 | 120
Menu Inheritance | Ilia | 19.04. ¦¦ 10:30 | 150
GUI design | Mikaeil | 19.04. ¦¦ 16:30 | 180
Website implementation | Angel | 19.04. ¦¦ 12:00 | 120
Group meeting | Group | 20.04. ¦¦ 10:30 | 165 | Week 10
GUI design | Mikaeil | 20.04. ¦¦ 13:00 | 180
Website design | Angel | 21.04. ¦¦ 12:00 | 120
Group meeting | Group | 22.04. ¦¦ 13:30 | 120
Setup document | Angel | 23.04. ¦¦ 19:00 | 30
Website | Angel | 23.04. ¦¦ 19:30 | 100
Setup document review | Georgi | 23.04. ¦¦ 21:00 | 60
Database SQL | Ilia | 23.04. ¦¦ 20:00 | 120
GUI design | Mikaeil | 23.04. ¦¦ 13:00 | 180
Classes | Ilia | 23.04. ¦¦ 22:00 | 120
Schedule and website review | Georgi and Angel | 24.04. ¦¦ 11:30 | 80
Setup document | Georgi | 24.04. ¦¦ 12:40 | 30
Group meeting: Schedule, Setup document, Website, GitHub | Group | 24.04. ¦¦ 16:30 | 90
Database | Mikaeil | 24.04. ¦¦ 17:00 | 60
Database research | Georgi | 25.04. ¦¦ 12:00 | 180
Programming | Mikaeil | 26.04. ¦¦ 12:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 28.04. ¦¦ 18:30 | 60 | Week 11
Website functionality | Angel | 29.04. ¦¦ 20:00 | 120
Website functionality | Angel | 30.04. ¦¦ 16:00 | 120
Database implementation | Georgi | 01.05. ¦¦ 12:00 | 60
Website functionality | Angel | 01.05. ¦¦ 13:00 | 180
Website functionality | Angel | 02.05. ¦¦ 12:00 | 240
Database connection | Georgi and Ilia | 03.05. ¦¦ 16:30 | 60
Website functionality | Angel | 03.05. ¦¦ 17:00 | 120
SQL adaptation | Ilia | 04.05. ¦¦ 20:30 | 75
Database connection | Angel Georgi and Ilia | 05.05. ¦¦ 18:00 | 60
Database | Ilia | 06.05. ¦¦ 13:00 | 90
Website | Angel | 06.05. ¦¦ 14:00 | 120
SQL adaptation | Ilia | 06.05. ¦¦ 15:00 | 50
Database review and foreign key structure | Georgi | 07.05. ¦¦ 12:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 08.05. ¦¦ 12:00 | 60
Website | Angel | 08.05. ¦¦ 13:00 | 120
Process report | Georgi | 09.05. ¦¦ 18:00 | 120
Website | Angel | 09.05. ¦¦ 13:00 | 120
Website | Angel | 10.05. ¦¦ 13:00 | 180
PHP ticket func | Angel and Ilia | 11.05. ¦¦ 11:00 | 120 | Week 12
Base documents (agenda, notes and meeting) | Georgi | 11.05. ¦¦ 12:00 | 60
RFID | Ilia | 12.05. ¦¦ 16:00 | 180
Website functionality | Angel | 12.05. ¦¦ 19:00 | 60
Website functionality | Angel Georgi and Ilia | 12.05. ¦¦ 20:00 | 120
Process report | Georgi | 14.05. ¦¦ 16:00 | 60
Database to class conversion | Ilia | 14.05. ¦¦ 21:00 | 180
Group meeting | Group | 15.05. ¦¦ 21:00 | 120
Class revision | Ilia and Georgi | 15.05. ¦¦ 12:00 | 60
Group meeting | Mikaeil Angel and Ilia | 16.05. ¦¦21:00 | 60
Appointments GUI | Georgi | 16.05. ¦¦ 16:00 | 90
Renting GUI | Georgi | 17.05. ¦¦ 12:00 | 120
Group meeting | Group | 17.05. ¦¦ 21:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 18.05. ¦¦ 12:00 | 60 | Week 13
Group meeting | Group | 18.05. ¦¦ 14:00 | 120
Website functionality | Angel | 18.05. ¦¦ 16:00 | 60
C# Admin GUI | Mikaeil | 18.05. ¦¦ 15:00 | 280
Shop order confirm | Ilia | 19.05. ¦¦ 17:00 | 60
Database relations check | Ilia | 19.05. ¦¦ 18:20 | 5
Website functionality | Angel | 19.05. ¦¦ 16:00 | 60
GUI Logic and design | Georgi | 19.05. ¦¦ 15:00 | 120
Group meeting | Group | 19.05. ¦¦ 21:00 | 120
Website functionality | Mikaeil | 20.05. ¦¦ 20:00 | 300
Shop order confirm | Ilia | 20.05. ¦¦ 00:00 | 60
Ticket functionality | Angel | 20.05. ¦¦ 21:00 | 60
Ticket and twitter func | Angel | 22.05. ¦¦ 12:00 | 120
Database logging | Ilia | 27.05. ¦¦ 13:00 | 120
Base documents (agenda, notes and meeting) | Georgi | 18.05. ¦¦ 12:00 | 60
Search at shops | Ilia | 24.05. ¦¦ 20:00 | 30 | Week 14
Application division | Ilia | 24.05. ¦¦ 16:00 | 60
Renting logic | Georgi | 26.05. ¦¦ 12:00 | 120
Website paypal doc | Mikaeil | 25.05. ¦¦ 12:00 | 300
Database Integrity | Ilia | 26.05. ¦¦ 13:00 | 60
Classes Integrity | Ilia | 26.05. ¦¦ 18:30 | 60
Booking overview | Ilia | 28.05. ¦¦ 13:30 | 60
Renting GUI | Georgi | 28.05. ¦¦ 12:00 | 120
Booking application | Ilia | 28.05. ¦¦ 20:00 | 150
GUI issues | Ilia | 29.05. ¦¦ 00:00 | 120
Renting logic | Georgi | 31.05. ¦¦ 16:00 | 120